## Journal
Apprenti.e | Néo Darbellay |  | Durée total (h ou p) |  | 56p
Classe ou Groupe | CID2A/GRP2C |  | Experts |  | -
Chef.fe de Projet | S. Oliveira |  | Bulle / Domaine / Module |  | INF / DEV / P_Prod
Sujet | Craft Me Up
Tâches | Dates | Durées [min] | Explications | Etats | Date de fin | Sources, liens, références, commits …
Setup | 2025-11-03 | 30 | Setting up the work environment | Finished | 14:10 | https://github.com/Jonathan150408/Craft-Me-Up
Explanations |  | 35 | Explanation of the code | Finished | 14:45
Class diagram |  | 60 | Creating a diagram for every class | Not finished | 15:45 | Not everything is done, will be finished next session
Bilan du jour : | Jour 1 | Durée totale: | 125
Class diagram | 2025-11-04 | 30 | Finishing the class diagrams | Finished | 8:45
Writing |  | 50 | Writing the product specifications | Finished | 9:35 | This may get changed later, as this was done without Jonathan's approval, as he wasn't there
Backlog |  | 25 | Writing 4 new issues | Finished | 10:15 | This was done in a .txt file originally, as the GitHub Project wasn't set up yet and I cannot create it
Designing |  | 35 | Designing 4 images for the new issues | Finished | 10:50
Coding |  | 35 | Started working on the code optimization | Not finished | 11:25 | Not everything is done, will be finished next session
Bilan du jour : | Jour 2 | Durée totale: | 175
Debating | 2025-11-10 | 45 | Debating on code optimization | Finished | 13:55 | This was used for the new class diagrams
Backlog |  | 55 | Writing the fifth issue & adding the previous ones to GitHub Project | Finished | 15:10 | This took a while, as GitHub decided to disable issues in the project.
Coding |  | 45 | Continuing code optimization | Finished | 15:55 | All progress here has been reset as the PC's power source got turned off by a classmate.
Bilan du jour : | Jour 3 | Durée totale: | 145
Other | 2025-11-11 |  | Working on a presentation for another class | Finished | 9:25 | I'm not adding the duration, as this wasn't part of the project. However, it did take up some of the allocated project time. I'll take time off during a weekend to compensate for it.
Coding |  | 105 | Continuing code optimization | Finished | 11:25 | Character.cs, Projectile.cs, Obstacle.cs
Bilan du jour : | Jour 4 | Durée totale: | 105
Coding | 2025-11-17 | 105 | Continuing code optimization | Finished | 15:10 | Enemy.cs, along with fixes for Character, Projectile and Obstacle.
Coding |  | 10 | Analyzing the code to see if I missed anything that could be optimized | Finished | 15:20
Coding |  | 25 | Implementing Jonathan's optimisation | Finished | 15:45 | Still needs some fixing
Bilan du jour : | Jour 5 | Durée totale: | 140
Coding | 2025-11-18 | 100 | Fixing rendering issues with the new system | Finished | 10:30 | Since the optimization was so big, a lot of things broke and had to be changed There are still some issues, but I'll need Jonathan to help out
Coding |  | 45 | Fixing projectiles with the new system | Finished | 11:15 | They shoot again, but have some issues that will need more fixing
Coding |  | 10 | Re-adding health bar visuals (obstacle, characters) | Finished | 11:25
Bilan du jour : | Jour 6 | Durée totale: | 155
Coding |  | 10 | Fixing an issue with zombies teleporting to 0 0 | Finished | 13:20
Coding |  |  | Testing the old app to see if it was easier to fix than the current one | In the work
Bilan du jour : | Jour 7 | Durée totale: | 10
Bilan du jour : | Jour 8 | Durée totale: | 0
Total en heures |  | 14.2
Si nécessaire, [ Copier ] & [ Insérer ] un ou des jours supplémentaires avant la ligne du total

## Restrictions
Finished | Not finished | In the work | Not started